## Health Check
Agile Health Check
Quarterly team health scoring across delivery, process and culture dimensions
Dimension | Question | Team | Score (1-5) | Trend vs Last Quarter | Owner | Action Needed | Target Date | Notes
Sprint Predictability | Are we consistently completing what we commit to each sprint? | Platform Squad | 4 | Up | Scrum Master | Continue current cadence
Backlog Health | Is the backlog refined far enough ahead to avoid mid-sprint surprises? | Platform Squad | 3 | Flat | Product Owner | Increase refinement frequency to twice weekly | 2026-02-15
Team Morale | Does the team feel able to raise concerns without friction? | Platform Squad | 4 | Up | Scrum Master | Continue retro format
Technical Debt | Is technical debt visible and actively being addressed? | Platform Squad | 2 | Down | Engineering Lead | Allocate 15% capacity per sprint to debt paydown | 2026-02-01 | Flagged in last two retros
Dependency Management | Are cross-team dependencies identified before they block work? | Platform Squad | 3 | Flat | Programme Manager | Introduce dependency board in planning | 2026-02-08
Stakeholder Alignment | Do stakeholders have a clear and current view of progress? | Platform Squad | 4 | Up | Programme Manager | Maintain current reporting rhythm
Definition of Done | Is the Definition of Done consistently applied across the team? | Platform Squad | 3 | Up | Scrum Master | Re-align DoD in next retro | 2026-02-10
Release Confidence | Does the team feel confident in release quality before go-live? | Platform Squad | 4 | Flat | QA Lead | Continue current test gate process

## Summary
Health Check Summary
Average Score | 3.375
Dimensions Below 3 | 1
Dimensions Trending Down | 1