## Change Control Log
Change Control Log
Tracks every requested change to scope, schedule or budget with impact and approval status
Change ID | Date Raised | Raised By | Description | Reason for Change | Impact: Scope | Impact: Schedule | Impact: Budget | Approval Status | Approved By | Date Decided
CR001 | 2026-01-10 | Product Owner | Add a new export format to the reporting module | Client requested during UAT to support their existing workflow | Minor | +3 days | None | Approved | Sponsor | 2026-01-12
CR002 | 2026-01-18 | Engineering Lead | Upgrade test automation framework mid-sprint | Current framework lacks support for new API version | None | +5 days | None | Approved | Programme Manager | 2026-01-19
CR003 | 2026-01-25 | Client Stakeholder | Extend payment gateway to support an additional currency | Business requirement surfaced after initial scope was set | Moderate | +8 days | +€4,000 | Pending

## Summary
Change Control Summary
Total Changes Logged | 3
Approved | 2
Pending | 1
Rejected | 0