## Decision Rights Matrix
Decision Rights Matrix
Who decides, who is consulted, who is informed, by decision type — D / R / C / I
D = Decides R = Responsible (executes) C = Consulted before decision I = Informed after decision
Decision Type | Example | Engineering Lead | Product Owner | Programme Manager | Sponsor / Steering | Escalation Path | Notes
Scope change | Adding a new feature mid-sprint | C | R | D | I | Programme Manager to Sponsor if budget impact
Resource conflict | Two workstreams need the same engineer | C | I | D | I | Programme Manager decides; escalate if unresolved in 48h
Go / No-Go release | Release readiness sign-off | R | C | D | C | Steering Committee for high-risk releases
Budget reallocation | Shifting spend between workstreams | I | I | C | D | Sponsor approval required above threshold
Technical architecture | Choosing between two technical approaches | D | C | I | I | Engineering Lead decides; informs Programme Manager
Vendor selection | Choosing a third-party vendor or tool | C | C | R | D | Sponsor sign-off required for contracts