## Dependency Map
Dependency Map
Tracks cross-team and external dependencies, what depends on what, and the risk of a slip
Dependency ID | Dependent Item | Depends On | Owning Team | Dependency Type | Direction | Due Date | Status | Risk if Delayed | Mitigation | Notes
DEP001 | Feature freeze for v12 release | Localisation vendor delivery for all 6 languages | Release Management | External | Inbound | 2026-02-01 | At Risk | GA date slips by up to 2 weeks | Weekly vendor check-in; escalation path agreed with vendor lead
DEP002 | Payment integration go-live | Sandbox access from third-party payment gateway | Development | External | Inbound | 2026-01-20 | On Track | Testing cannot begin without sandbox access | Access confirmed; credentials received
DEP003 | UAT sign-off | Completion of regression test automation | QA | Internal | Inbound | 2026-02-25 | At Risk | UAT start date slips by one sprint | Backfill QA resource requested
DEP004 | Workstream B development | API contract finalised by Workstream A | Development | Internal | Inbound | 2026-01-30 | On Track | Workstream B blocked from starting integration work | Contract reviewed and signed off this week

## Summary
Dependency Summary
Total Dependencies | 4
On Track | 2
At Risk | 2
Blocked | 0
External Dependencies | 2