## Survey Results
Employee Engagement Survey Results
Category scores compared against the previous survey cycle, with gap to benchmark
Category | Sample Question | This Cycle Score (1-5) | Last Cycle Score (1-5) | Change | Benchmark Target | Gap to Target | Priority for Action
Leadership & Direction | I have confidence in the direction set by leadership | 4.1 | 3.8 | 0.3 | 4 | -0.1 | Low
Career Growth | I see a clear path for growth in my role | 3.2 | 3 | 0.2 | 3.8 | 0.6 | High
Recognition | My contributions are recognised appropriately | 3.5 | 3.3 | 0.2 | 3.8 | 0.3 | Medium
Work-Life Balance | I am able to maintain a healthy work-life balance | 3.9 | 3.6 | 0.3 | 4 | 0.1 | Medium
Team Collaboration | My team collaborates effectively across roles | 4.3 | 4 | 0.3 | 4 | -0.3 | Low
Psychological Safety | I feel safe raising concerns without negative consequences | 3.7 | 3.9 | -0.2 | 4 | 0.3 | Medium
Tools & Resources | I have the tools and resources I need to do my job well | 3.4 | 3.1 | 0.3 | 3.8 | 0.4 | Medium
Overall Engagement | Overall, I am engaged and motivated at work | 3.8 | 3.5 | 0.3 | 4 | 0.2 | Medium

## Action Plan
Improvement Action Tracker
Actions raised in response to survey results, owned and tracked to completion
Category | Action | Owner | Priority | Status | Start Date | Target Date | Progress (%) | Impact Expected
Career Growth | Introduce quarterly career conversations separate from performance reviews | Programme Manager | High | In Progress | 2026-01-15 | 2026-03-31 | 40% | Improve perceived growth path clarity
Tools & Resources | Run audit of tooling gaps raised in open text feedback | Engineering Lead | High | In Progress | 2026-01-20 | 2026-02-28 | 60% | Close gaps before next survey cycle
Recognition | Launch lightweight peer recognition mechanism | Programme Manager | Medium | Not Started | 2026-02-01 | 2026-04-01 | 0% | Increase day to day recognition visibility
Psychological Safety | Run culture code workshop focused on raising concerns safely | Programme Manager | Medium | Completed | 2025-11-01 | 2025-12-15 | 100% | Reverse the score decline seen this cycle

## Summary
Engagement Summary
Quick view of survey movement and action plan progress
Average Score This Cycle | 3.74
Average Score Last Cycle | 3.53
Categories Improved | 7
Categories Declined | 1
High Priority Gaps | 1
Actions In Progress | 2
Actions Completed | 1