## Gantt Chart
Programme Gantt Chart
Task schedule with week-by-week timeline bars. Enter Start Date and Duration; bars shade automatically.
[6 empty] | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20
Task | Owner | Start Date | End Date | Duration (days) | % Complete | Wk 1 05 Jan | Wk 2 12 Jan | Wk 3 19 Jan | Wk 4 26 Jan | Wk 5 02 Feb | Wk 6 09 Feb | Wk 7 16 Feb | Wk 8 23 Feb | Wk 9 02 Mar | Wk 10 09 Mar | Wk 11 16 Mar | Wk 12 23 Mar | Wk 13 30 Mar | Wk 14 06 Apr | Wk 15 13 Apr | Wk 16 20 Apr
Discovery and requirements | K. Ramachandran | 2026-01-05 | 2026-01-16 | 11 | 100%
Architecture and design | Engineering Lead | 2026-01-12 | 2026-01-30 | 18 | 90%
Development - Workstream A | Dev Team A | 2026-01-19 | 2026-02-20 | 32 | 60%
Development - Workstream B | Dev Team B | 2026-01-26 | 2026-02-27 | 32 | 40%
QA and Test Automation | QA Lead | 2026-02-09 | 2026-03-06 | 25 | 15%
UAT | Business Analyst | 2026-03-02 | 2026-03-13 | 11 | 0%
Go-live and hypercare | Release Manager | 2026-03-16 | 2026-03-27 | 11 | 0%

## Resource Allocation
Resource Allocation Tracker
Weekly capacity allocation by resource, percentage of time committed to each workstream
Resource Name | Role | Total Capacity (%) | Workstream A (%) | Workstream B (%) | QA / Testing (%) | Admin / Meetings (%) | Total Allocated (%) | Over/Under Allocated | Available Capacity (%) | Notes
K. Ramachandran | Programme Manager | 100% | 20% | 20% | 10% | 30% | 80% | Under | 20%
Engineering Lead | Architecture | 100% | 50% | 30% | 0% | 10% | 90% | Under | 10%
Dev Team A (avg) | Development | 100% | 80% | 0% | 0% | 10% | 90% | Under | 10%
Dev Team B (avg) | Development | 100% | 0% | 80% | 0% | 10% | 90% | Under | 10%
QA Lead | Quality Assurance | 100% | 10% | 10% | 70% | 5% | 95% | Under | 5%
Business Analyst | UAT and Sign-off | 80% | 10% | 10% | 20% | 10% | 50% | Under | 30%