## KPI Tracker
KPI Tracker
Recurring delivery KPIs tracked against target, with automatic Red Amber Green status
Instructions: set a Target and Threshold for each KPI. Status calculates automatically: Green if Current meets target, Amber within threshold, Red beyond it.
KPI | Category | Target | Threshold (Amber Range) | Current | Status | Direction | Frequency | Owner | Trend vs Last Period | Notes
Sprint Completion Rate | Delivery | 90% | 10% | 88% | Amber | Higher | Sprint | Programme Manager | Up
Release Schedule Variance | Delivery | 10% | 5% | 11% | Amber | Lower | Quarterly | Release Manager | Down | Slight slip this quarter
OKR Completion Rate | Delivery | 85% | 10% | 90% | Green | Higher | Quarterly | Programme Manager | Up
Manual Regression Test Hours | Quality | 40 | 10 | 37 | Green | Lower | Per Release | QA Lead | Down | Automation expansion paying off
Critical Incidents Post Launch | Quality | 0 | 1 | 0 | Green | Lower | Per Release | QA Lead | Flat
Leadership Decision Turnaround (days) | Stakeholder | 5 | 1 | 5.5 | Amber | Lower | Monthly | Programme Manager | Flat
Backlog Estimation Variance | Delivery | 15% | 5% | 14% | Green | Lower | Quarterly | Product Owner | Up
Team Engagement Score (out of 5) | Culture | 4 | 0.3 | 3.9 | Amber | Higher | Quarterly | Programme Manager | Up

## Summary
KPI Summary
Total KPIs Tracked | 8
Green | 4
Amber | 4
Red | 0