## OKRs
OKR Tracker
Objectives and Key Results tracked quarterly, with progress bars and a 0 to 1.0 confidence score
Instructions: enter one Objective per group. Add 2 to 4 Key Results under each. Score Key Results 0.0 to 1.0 (0.7 is considered a strong result in OKR practice, not 1.0). Avoid more than 5 Objectives per quarter.
Type | Objective / Key Result | Owner | Metric / Target | Baseline | Current | Progress (%) | Confidence Score (0-1) | Notes
Objective 1: Improve release predictability and delivery throughput
Key Result | Increase sprint completion rate to 90% | Programme Manager | Sprint completion % | 72% | 88% | 88% | 0.7
Key Result | Deliver releases within 10% of committed dates | Release Manager | Schedule variance % | 22% | 11% | 80% | 0.6
Key Result | Reduce backlog refinement variance across 100+ items per quarter | Product Owner | Estimation variance % | 30% | 14% | 75% | 0.65
Objective 2: Strengthen quality and reduce manual testing effort
Key Result | Reduce manual regression testing effort by 40% | QA Lead | Manual test hours/cycle | 60 hrs | 37 hrs | 92% | 0.8
Key Result | Achieve zero critical incidents post launch | QA Lead | Critical incidents | 2 | 0 | 100% | 0.9
Objective 3: Improve stakeholder visibility and decision speed
Key Result | Reduce leadership decision turnaround time by 25% | Programme Manager | Avg decision time (days) | 8 days | 5.5 days | 70% | 0.6
Key Result | Maintain weekly steering reporting with zero missed cycles | Programme Manager | Reporting cadence adherence | N/A | 100% | 100% | 0.85

## Summary
OKR Summary
Average Progress | 86.43%
Average Confidence Score | 0.72857
Key Results Above 70% Progress | 7