## 📖 Guide
PROGRAMME FINANCIAL MANAGEMENT TOOLKIT
A practical learning and working tool for Project, Programme and Portfolio Managers
COLOUR CODING LEGEND
Sample | Blue text on light blue = INPUT CELL — change these values
Sample | Black text on white = FORMULA — do not overwrite
Sample | Light blue background = TOTAL / SUMMARY row
Sample | Green background = positive / on track
Sample | Red/amber background = warning / over budget
Sample | Grey background = label / description
WORKBOOK CONTENTS
Sheet | What You Will Learn and Do
1. Budget Planner | Build your project budget from scratch. Separate CapEx and OpEx. Add contingency and management reserve. See your full budget baseline.
2. CapEx vs OpEx | Learn the difference with real software project examples. Classify your spend. See tax and accounting implications.
3. EVM Dashboard | Earned Value Management in action. Enter your planned, actual and earned values. Get CPI, SPI, EAC and forecasts automatically.
4. Business Case | Build a full business case with NPV, IRR, ROI and Payback Period. Change assumptions and see impact instantly.
5. Monthly Finance Report | A real monthly financial report template. Track actuals vs budget. Explain variances. Forecast to completion.
6. Risk Reserve Calc | Calculate contingency reserve using Expected Monetary Value (EMV). Understand known unknowns.
HOW TO USE THIS WORKBOOK
Step 1 | Start with Sheet 1 (Budget Planner) — enter your project details and build your baseline budget.
Step 2 | Use Sheet 2 (CapEx vs OpEx) to correctly classify every cost line — this matters for your Finance team.
Step 3 | As your project runs, update Sheet 3 (EVM Dashboard) monthly to track performance and forecast.
Step 4 | Use Sheet 4 (Business Case) when seeking investment approval or reviewing project viability.
Step 5 | Sheet 5 is your monthly report — complete it before every finance review or steering committee.
Step 6 | Sheet 6 helps you justify your contingency budget to sponsors with data, not guesswork.

## 1. Budget Planner
PROJECT BUDGET PLANNER — Software Delivery Project
PROJECT INFORMATION
Project Name | Customer Portal Redesign
Programme | Digital Transformation Programme
Project Manager | Your Name
Start Date | 01/04/2025
End Date | 31/03/2026
Budget Owner | Head of Technology
COST CATEGORY / ITEM | Type | Q1 (£) | Q2 (£) | Q3 (£) | Q4 (£) | Total (£) | % of Budget
CAPITAL EXPENDITURE (CapEx)
Software Development (bespoke build) | CapEx | 45000 | 60000 | 55000 | 40000 | 200000 | 34.54%
UX Design and Prototyping | CapEx | 12000 | 8000 | 0 | 0 | 20000 | 3.454%
Infrastructure Setup (servers, cloud arch) | CapEx | 18000 | 5000 | 5000 | 0 | 28000 | 4.836%
Third-party Integrations (one-off build) | CapEx | 8000 | 12000 | 10000 | 0 | 30000 | 5.181%
Security Architecture and Pen Testing | CapEx | 0 | 0 | 15000 | 5000 | 20000 | 3.454%
Data Migration (one-off) | CapEx | 0 | 10000 | 8000 | 0 | 18000 | 3.109%
TOTAL CapEx |  | 83000 | 95000 | 93000 | 45000 | 316000 | 54.58%
OPERATING EXPENDITURE (OpEx)
Internal Staff — Product Owner (FTE allocation) | OpEx | 15000 | 15000 | 15000 | 15000 | 60000 | 10.36%
Internal Staff — Business Analyst | OpEx | 12000 | 12000 | 12000 | 12000 | 48000 | 8.29%
Contractor — Senior Developer (day rate) | OpEx | 25000 | 25000 | 20000 | 10000 | 80000 | 13.82%
Contractor — QA Engineer | OpEx | 0 | 10000 | 15000 | 10000 | 35000 | 6.045%
SaaS Licences (project tooling) | OpEx | 2000 | 2000 | 2000 | 2000 | 8000 | 1.382%
Cloud Hosting (during build) | OpEx | 1500 | 1500 | 1500 | 1500 | 6000 | 1.036%
Training and Enablement | OpEx | 5000 | 0 | 5000 | 0 | 10000 | 1.727%
Travel and Expenses | OpEx | 1000 | 1000 | 1000 | 1000 | 4000 | 0.6908%
Programme Management Office (PMO) overhead | OpEx | 3000 | 3000 | 3000 | 3000 | 12000 | 2.073%
TOTAL OpEx |  | 64500 | 69500 | 74500 | 54500 | 263000 | 45.42%
RESERVES
Contingency Reserve (known unknowns — see Sheet 6) | Reserve | 0 | 0 | 0 | 0 | 0
Management Reserve (unknown unknowns — sponsor held) | Reserve | 0 | 0 | 0 | 0 | 0
💡 TIP: Contingency Reserve is typically 5-15% of project cost for known risks. Management Reserve is 3-7% held by the sponsor. See Sheet 6 to calculate these properly using EMV.
TOTAL PROJECT BUDGET (Baseline) |  | 147500 | 164500 | 167500 | 99500 | 579000
BUDGET SUMMARY
Total CapEx | 316000 | 54.58%
Total OpEx | 263000 | 45.42%
Total Reserves | 0 | 0%
TOTAL BUDGET | 579000 | 100%

## 2. CapEx vs OpEx
CapEx vs OpEx — Understanding the Difference (Software Project Context)
WHAT IS CAPEX? |  |  | WHAT IS OPEX?
CapEx = money spent to BUILD or ACQUIRE an asset that will provide value over multiple years. In software: building a bespoke application, one-off data migration, infrastructure setup. Accounting treatment: Goes on the Balance Sheet as an asset. The cost is spread (depreciated or amortised) over the useful life of the asset — typically 3-5 years for software. Example: You spend £200,000 building a customer portal. That £200,000 becomes an intangible asset and you write off £40,000 per year over 5 years. |  |  | OpEx = money spent on RUNNING and OPERATING the business day to day. In software: cloud hosting fees, SaaS subscriptions, support staff salaries, training. Accounting treatment: Goes straight to the Profit and Loss (P&L) statement in the period it is spent. It reduces profit immediately. Example: You pay £2,000 per month for AWS hosting. That £24,000 per year hits your P&L directly — it is fully expensed in the year it is spent.
WHY THIS MATTERS TO YOU AS A PM / PROGRAMME MANAGER
1. Your organisation likely has SEPARATE BUDGETS for CapEx and OpEx. Misclassifying spend can mean you blow one budget while appearing under on another — causing real problems with Finance. 2. Cloud migrations shift spend from CapEx (building/buying servers) to OpEx (monthly cloud subscriptions). This is a massive financial shift that affects the P&L and requires stakeholder management. 3. Contractors doing billable BUILD work can often be classified as CapEx. Contractors doing support or BAU are OpEx. This distinction affects how you present cost to Finance. 4. Getting this wrong causes tax and audit issues. Finance will push back hard. Understanding it builds your credibility enormously.
COST CLASSIFIER — COMMON SOFTWARE PROJECT SPEND
Cost Item | Typical Classification | Amount (£) | Reason / Rule of Thumb
Bespoke software development (new product) | CapEx | 120000 | Creating a new asset with future value — meets capitalisation criteria
Enhancement adding new functionality | CapEx | 45000 | Adding capabilities = extending the asset life or value
Bug fixing and maintenance | OpEx | 18000 | Maintaining existing functionality — not creating new value
Cloud SaaS subscription (e.g. Jira, Salesforce) | OpEx | 8400 | Recurring service fee — no asset ownership, fully expensed
On-premise perpetual software licence | CapEx | 25000 | You OWN the licence — it is an intangible asset on balance sheet
AWS / Azure hosting (monthly) | OpEx | 24000 | Recurring cloud cost — operational expense, no asset created
One-off data migration | CapEx | 30000 | Directly enables the new asset — capitalised as part of build cost
Ongoing data management post-launch | OpEx | 12000 | Business as usual operational activity
Contractor building the product | CapEx | 80000 | Their time directly contributes to the asset being built
Contractor doing support / hypercare | OpEx | 20000 | Support is operational — not building new capability
Staff training on new system | OpEx | 6000 | People cost — generally not capitalisable under most standards
UX research for new product | CapEx | 15000 | Direct cost of developing the new asset
Server hardware purchase (on-prem) | CapEx | 40000 | Physical asset — depreciated over useful life (typically 3-5 years)
Annual software support and maintenance contract | OpEx | 9600 | Ongoing support — not creating new value
Pen testing / security audit (one-off at launch) | CapEx | 12000 | Directly related to launching the new asset
Pen testing / security audit (annual recurring) | OpEx | 8000 | Recurring operational activity
TOTAL CapEx in this list |  | 367000
TOTAL OpEx in this list |  | 106000
CapEx as % of Total Spend |  | 77.59%

## 3. EVM Dashboard
EARNED VALUE MANAGEMENT (EVM) DASHBOARD — Software Project Tracker
EVM QUICK REFERENCE
Metric | Formula |  |  | What it Tells You
PV — Planned Value | PV |  |  | The budgeted cost of work SCHEDULED to be done by this point. What did you PLAN to spend?
EV — Earned Value | EV |  |  | The budgeted cost of work ACTUALLY COMPLETED. What is the COMPLETED work WORTH?
AC — Actual Cost | AC |  |  | The ACTUAL cost incurred for work completed. What did you ACTUALLY SPEND?
CV — Cost Variance | CV |  |  | EV minus AC. Positive = under budget. Negative = over budget.
SV — Schedule Variance | SV |  |  | EV minus PV. Positive = ahead of schedule. Negative = behind schedule.
CPI — Cost Performance Index | CPI |  |  | EV divided by AC. Greater than 1 = efficient. Less than 1 = overspending per pound of value delivered.
SPI — Schedule Performance Index | SPI |  |  | EV divided by PV. Greater than 1 = ahead. Less than 1 = behind schedule.
EAC — Estimate at Completion | EAC |  |  | BAC divided by CPI. Forecasted FINAL cost based on current efficiency.
ETC — Estimate to Complete | ETC |  |  | EAC minus AC. How much MORE you need to spend to finish.
VAC — Variance at Completion | VAC |  |  | BAC minus EAC. Positive = will finish under budget. Negative = will overspend.
PROJECT SETUP — INPUTS
Project Name | Customer Portal Redesign
Budget at Completion (BAC) | 550000
Total Project Duration (months) | 12
Reporting Month (enter 1-12) | 6
MONTHLY DATA ENTRY — Enter your PV, EV and AC each month
Metric | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
PV — Planned Value (£) | 45833 | 91667 | 137500 | 183333 | 229167 | 275000 | 320833 | 366667 | 412500 | 458333 | 504167 | 550000
EV — Earned Value (£) | 40000 | 82000 | 128000 | 168000 | 210000 | 248000
AC — Actual Cost (£) | 48000 | 98000 | 150000 | 195000 | 245000 | 295000
CALCULATED PERFORMANCE METRICS — Auto-calculated, do not edit
Metric | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
CV — Cost Variance (£) | -8000 | -16000 | -22000 | -27000 | -35000 | -47000
SV — Schedule Variance (£) | -5833 | -9667 | -9500 | -15333 | -19167 | -27000
CPI — Cost Performance Index | 0.83333 | 0.83673 | 0.85333 | 0.86154 | 0.85714 | 0.84068
SPI — Schedule Performance Index | 0.87273 | 0.89454 | 0.93091 | 0.91637 | 0.91636 | 0.90182 | 0 | 0 | 0 | 0 | 0 | 0
CURRENT PERIOD DASHBOARD
Metric | Value | Status | What This Means
Budget at Completion (BAC) | 550000 |  | Fixed total budget for the project
Reporting Month | 6 |  | Current month of project
Current PV (this month) | 275000 |  | What you planned to have spent by now
Current EV (this month) | 248000 |  | Value of work actually completed
Current AC (this month) | 295000 |  | What you actually spent
Cost Variance (CV) | -47000 | ⚠️ Over Budget | Positive = under budget
Schedule Variance (SV) | -27000 | ⚠️ Behind | Positive = ahead of schedule
CPI | 0.84068 | ⚠️ Overspending | Above 1.0 = efficient spend
SPI | 0.90182 | ⚠️ Behind | Above 1.0 = ahead of schedule
EAC — Forecast Final Cost | 654233.871 |  | Predicted total cost at current CPI
ETC — Cost to Complete | 359233.871 |  | How much more you need to spend
VAC — Variance at Completion | -104233.871 | 🚨 Will Overspend | Positive = will finish under budget

## 4. Business Case
BUSINESS CASE FINANCIAL MODEL — NPV, IRR, ROI and Payback Period
KEY ASSUMPTIONS (change these — everything updates automatically)
Assumption | Value | Notes
Discount Rate (WACC / hurdle rate) | 8% | The minimum return your organisation expects. Change this to your company's rate.
Project Duration (years) | 5 | How many years you are modelling including build and benefit years
Build Phase (years) | 1 | How long it takes to build before benefits start flowing
Annual Benefit Growth Rate | 5% | How much benefits grow each year after year 1
Annual Cost Inflation Rate | 3% | How much ongoing costs increase each year
INVESTMENT COSTS AND BENEFITS — Enter your numbers (£)
Item | Year 0 (Build) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
COSTS
Software Development (CapEx) | 200000 | 0 | 0 | 0 | 0 | 0
Infrastructure Setup (CapEx) | 30000 | 0 | 0 | 0 | 0 | 0
Internal Staff Time (OpEx) | 50000 | 20000 | 20000 | 20000 | 20000 | 20000
Ongoing Cloud Hosting (OpEx) | 0 | 18000 | 18000 | 18000 | 18000 | 18000
Support and Maintenance (OpEx) | 0 | 25000 | 25000 | 25000 | 25000 | 25000
Licence Fees (OpEx) | 0 | 12000 | 12000 | 12000 | 12000 | 12000
TOTAL COSTS | 280000 | 75000 | 75000 | 75000 | 75000 | 75000
BENEFITS
Revenue increase (new digital sales channel) | 0 | 80000 | 84000 | 88200 | 92610 | 97241
Cost savings — manual process elimination | 0 | 40000 | 42000 | 44100 | 46305 | 48620
Cost savings — reduced call centre volume | 0 | 25000 | 26250 | 27563 | 28941 | 30388
Productivity gain — staff time saved | 0 | 15000 | 15750 | 16538 | 17364 | 18233
Risk reduction (compliance cost avoidance) | 0 | 20000 | 20000 | 20000 | 20000 | 20000
TOTAL BENEFITS | 0 | 180000 | 188000 | 196401 | 205220 | 214482
NET CASH FLOW (Benefits minus Costs) | -280000 | 105000 | 113000 | 121401 | 130220 | 139482
Cumulative Cash Flow | -280000 | -175000 | -62000 | 59401 | 189621 | 329103
Discount Factor (at C4) | 1 | 0.92593 | 0.85734 | 0.79383 | 0.73503 | 0.68058
Present Value of Cash Flow | -280000 | 97222.2222 | 96879.2867 | 96372.0279 | 95715.5874 | 94929.1055
KEY FINANCIAL METRICS — DECISION MAKING INDICATORS
Metric | Value | Decision Rule | Interpretation
NPV — Net Present Value | 201118.2297 | Positive NPV = invest. Negative = reject. | Sum of all future cash flows discounted to today's money. The most rigorous financial measure.
Total Investment (undiscounted) | 655000 | Lower = better for same return | Total cash out regardless of timing
Total Benefits (undiscounted) | 984103 | Higher = better | Total cash in regardless of timing
ROI — Return on Investment | 50.24% | Positive ROI = worthwhile | Simple measure — does not account for time value of money
IRR — Internal Rate of Return | 31.07% | Must exceed hurdle rate (C4) | The discount rate at which NPV = zero. Higher = more attractive investment.
Payback Period | 3.5107 | Shorter = less risk | How many years until cumulative benefits exceed costs. Simple but ignores time value.
Benefit Cost Ratio | 1.5024 | Above 1.0x = viable | For every £1 spent, how many £ of benefit returned. Above 1.5x is typically strong.

## 5. Monthly Finance Report
MONTHLY PROJECT FINANCE REPORT
REPORT DETAILS
Project Name | Customer Portal Redesign
Reporting Period | October 2025
Project Manager | Your Name
Budget Holder | Head of Technology
Report Prepared By | Your Name
Report Date | 31/10/2025
OVERALL STATUS
Area | RAG Status | Commentary
Overall Financial Status | AMBER | Overspending in development. Contingency being assessed.
Budget Status | AMBER | Running 7% over plan due to additional contractor days
Forecast Status | RED | EAC exceeds baseline. Change request being raised.
Schedule Status | AMBER | 2 weeks behind plan. Additional sprint added.
FINANCIAL PERFORMANCE — PERIOD AND CUMULATIVE
Cost Category | Full Year Budget (£) | YTD Budget (£) | YTD Actuals (£) | Variance (£) | Variance Commentary
Software Development | 200000 | 100000 | 112000 | -12000 | Additional sprint required due to scope change in auth module
UX and Design | 20000 | 20000 | 18500 | 1500 | Completed under budget — designer worked efficiently
Infrastructure | 28000 | 18000 | 19200 | -1200 | Minor overrun — additional load balancer required
QA and Testing | 35000 | 17500 | 16800 | 700 | On track — automated test suite reducing manual effort
Internal Staff (allocated) | 48000 | 24000 | 24000 | 0 | On plan — FTE allocation as agreed
Contractors | 75000 | 37500 | 45000 | -7500 | Over — 2 extra contractor days per sprint to address tech debt
SaaS Licences | 8000 | 5333 | 5333 | 0 | On plan
Cloud Hosting | 6000 | 4000 | 3800 | 200 | Slightly under — optimised instance sizing
Training | 10000 | 5000 | 3500 | 1500 | Under YTD — training deferred to Q3
Travel and Expenses | 4000 | 2667 | 2100 | 567 | Under — remote working reduced travel
PMO Overhead | 12000 | 8000 | 8000 | 0 | On plan
Contingency Used | 20000 | 0 | 5000 | -5000 | 5k drawn against contingency for auth module rework
TOTAL | 466000 | 242000 | 263233 | -21233
FORECAST TO COMPLETION
Metric | Amount (£) | Notes
Approved Budget (Baseline) | 466000 | The original signed-off budget
Forecast Cost at Completion (EAC) | 510000 | Best estimate of final total cost — update this each month
Forecast Variance (EAC minus Budget) | 44000 | Positive = over budget. Negative = saving.
Remaining Budget to Spend | 202767 | Approved budget less what has been spent
Remaining Forecast to Spend (ETC) | 202767 | EAC less what has been spent — how much more needed
ACTIONS AND DECISIONS REQUIRED
Action | Owner | Due Date | Status | Notes
Raise Change Request for auth module overspend | PM | 15/11/2025 | In Progress | Draft CR being reviewed by sponsor
Review contractor utilisation — reduce days if possible | PM / Delivery Lead | 01/11/2025 | Open | Assess if velocity target can be met with fewer contractor days
Approve drawdown of contingency reserve | Sponsor | 10/11/2025 | Open | £15k additional contingency required for remainder of project
Reforecast full year spend | PM / Finance BP | 30/11/2025 | Open | Full reforecast aligned to change request outcome

## 6. Risk Reserve Calc
CONTINGENCY RESERVE CALCULATOR — Expected Monetary Value (EMV)
WHAT IS EMV AND WHY DO YOU NEED IT?
EMV = Probability x Impact. It is the statistically expected financial impact of a risk. WHY THIS MATTERS: When you go to your sponsor and ask for contingency, saying "I want 10% just in case" will not impress Finance. But showing a risk-by-risk EMV analysis that totals to a specific number — with probability and impact for each risk — is credible and defensible. HOW TO USE THIS SHEET: List every identified risk. Estimate the probability (0-100%) of it happening and the financial impact if it does. The EMV is calculated automatically. The sum of all EMVs is your recommended contingency reserve. KEY CONCEPT: You are NOT saying every risk will happen. You are saying that across all your risks, statistically the expected financial exposure is £X. Some risks will materialise, many will not. The reserve covers the aggregate expected exposure.
RISK REGISTER WITH EMV — Add your project risks below
Risk Description | Category | Probability (%) | Financial Impact if it Occurs (£) | EMV (£) | Mitigation / Notes
Key developer leaves mid-project | Resource | 25% | 30000 | 7500 | Negotiate notice period. Identify backup resource. Knowledge transfer sessions planned.
Third-party API integration more complex than estimated | Technical | 40% | 25000 | 10000 | Spike planned in sprint 3. Fallback to manual integration if needed.
Scope creep from stakeholders | Scope | 60% | 20000 | 12000 | Change control process established. Backlog grooming weekly.
Infrastructure costs exceed estimate (cloud) | Financial | 30% | 15000 | 4500 | Cost alerts set in AWS. Monthly cloud spend review with architect.
Security vulnerabilities found in pen test | Technical | 35% | 18000 | 6300 | Security review in design phase. OWASP checklist applied throughout.
Business sponsor changes mid-project | Stakeholder | 20% | 25000 | 5000 | Governance documented. Decision log maintained for handover.
Data quality issues in migration | Technical | 45% | 12000 | 5400 | Data profiling exercise planned before migration sprint.
Regulatory change affects requirements | Compliance | 15% | 35000 | 5250 | Legal team engaged. Compliance review checkpoint at M4.
Performance does not meet SLA under load | Technical | 30% | 22000 | 6600 | Load testing included in QA plan. Performance benchmarks agreed.
Supplier delays on licence procurement | Commercial | 20% | 8000 | 1600 | Order placed 8 weeks early. Fallback open-source option identified.
User adoption lower than expected | Benefits | 40% | 30000 | 12000 | Change management plan in place. Champions identified in each business unit.
Add your own risk here | Category | 0% | 0 | 0
Add your own risk here | Category | 0% | 0 | 0
Add your own risk here | Category | 0% | 0 | 0
Add your own risk here | Category | 0% | 0 | 0
TOTAL EMV — Recommended Contingency Reserve |  |  |  | 76150
RESERVE SUMMARY AND RECOMMENDATION
Item | Amount (£) | Notes
Total Project Budget (from Budget Planner) | 466000 | Enter your total project budget here
EMV-based Contingency Reserve | 76150 | Calculated automatically from your risk register above
Contingency as % of Budget | 16.34% | Typically between 5% and 15% for software projects
Recommended Management Reserve (3-7% of budget) | 2330000% | Sponsor-held for unknown unknowns — adjust % as appropriate
TOTAL RECOMMENDED RESERVE | 99450 | Use this figure in your Budget Planner reserves section