## RAID Log
RAID Log Template
Risks, Assumptions, Issues and Dependencies — tracked with owner, impact and review date
ID | Type | Category | Description | Owner | Impact | Likelihood | Priority | Status | Raised Date | Review Date | Mitigation / Action | Notes
R001 | Risk | Technical | Third-party payment gateway integration may not meet go-live timeline | K. Ramachandran | High | Medium | High | Open | 2026-01-10 | 2026-01-24 | Escalate to vendor lead; build buffer sprint into plan | Reviewed weekly in steering
A001 | Assumption | Resourcing | Assumes two QA engineers remain allocated through UAT phase | Programme Manager | Medium | Low | Medium | Open | 2026-01-10 | 2026-02-07 | Confirm allocation with resourcing lead
I001 | Issue | Process | No existing change control process for this engagement | K. Ramachandran | High | High | High | In Progress | 2026-01-12 | 2026-01-20 | Stood up lightweight change control log this week | Resolved by Jan 20
D001 | Dependency | External | Localisation vendor delivery feeds into feature freeze milestone | Release Manager | Medium | Medium | Medium | Open | 2026-01-12 | 2026-02-01 | Weekly check-in scheduled with vendor

## Summary
RAID Log Summary
Total Risks | 1
Total Assumptions | 1
Total Issues | 1
Total Dependencies | 1
Open High Priority Items | 1