## Cover Summary
Steering Pack
Standard structure for programme steering committee reporting
Programme Name | Name of the programme
Reporting Period | e.g. Sprint 14, or Month of January 2026
Prepared By | Your name and role
Steering Date | Date of the steering meeting
Overall RAG Status | Green / Amber / Red
Executive Summary
Two or three sentences on overall progress this period, the single most important decision needed from this steering meeting, and anything leadership should know before the next reporting period.

## RAG by Workstream
RAG Status by Workstream
Status across each major workstream this reporting period
Workstream | Status | Progress Summary | Key Risk / Issue | Owner | Trend vs Last Period | Action Needed
Platform Engineering | Green | On track; sprint velocity stable | None material this period | Engineering Lead | Flat | None
QA and Test Automation | Amber | Regression suite expansion behind plan by one sprint | Resourcing gap on automation engineer | QA Lead | Down | Backfill resource or descope regression scope
Vendor Integration | Green | Third-party API integration complete and tested | None | Programme Manager | Up | None
Release Management | Amber | Feature freeze at risk by three days | Dependency on localisation vendor | Release Manager | Flat | Escalate vendor timeline this week

## Decisions Needed
Decisions Needed
Decisions requiring steering committee input this period
Decision | Context | Recommendation | Decision Owner | Status | Date Decided
Approve descope of two minor features | Integration risk threatens committed release date | Descope and ship stable; deferred scope tracked separately | Sponsor | Pending
Approve additional QA contractor | Regression suite expansion behind plan | Backfill for one sprint to recover schedule | Sponsor | Pending

## Top Risks
Top Risks This Period
Highest priority risks surfaced for steering visibility
Risk | Impact | Likelihood | Mitigation | Owner | Review Date
Localisation vendor delivery slipping | High | Medium | Weekly vendor check-in; escalation path agreed | Release Manager | 2026-02-05
Automation engineer resourcing gap | Medium | High | Backfill request submitted to resourcing | QA Lead | 2026-02-03